GAISSF® v1.0

Deployment Playbook

Step-by-Step Rollout, Production Transition and Operational Handover

| Field | Value |
| --- | --- |
| Document ID | GAISSF-IMP-011 |
| Version | 1.0 |
| Status | Final Publication Edition |
| Classification | Implementation guidance — informative |
| Publisher | ODA3 Institute |
| Legal entity | ODA3 Pvt Ltd |
| Authoritative normative source | GAISSF-NOR-001 |
| Control baseline | 59 controls across nine domains |
| Publication date | 29 June 2026 |

This playbook provides rollout guidance. It does not replace the normative framework, control catalogue, approved conformance profile, system safety case or organizational change-control process.

# Document Control

| Attribute | Controlled value |
| --- | --- |
| Title | GAISSF® v1.0 Deployment Playbook |
| Document ID | GAISSF-IMP-011 |
| Purpose | Provide a repeatable step-by-step deployment and rollout method |
| Primary audience | Program managers, security architects, AI engineers, platform teams, MLOps, DevSecOps, system owners, change managers, risk, compliance and assurance teams |
| Dependencies | GAISSF-NOR-001 through GAISSF-NOR-008, GAISSF-IMP-009 and GAISSF-IMP-010 |
| Classification | Informative implementation guidance |
| Precedence | GAISSF-NOR-001, GAISSF-NOR-004 and controlled conformance profiles prevail |
| Distribution | Public — Website and GitHub |

# Legal and Reliance Notice

© 2026 ODA3 Pvt Ltd. Published market-facing by ODA3 Institute.

GAISSF® is used as a framework mark. Third-party names and marks remain the property of their respective owners.

This playbook does not constitute legal, regulatory, safety, engineering, certification or audit advice. It does not create a legal safe harbour, establish a legal standard of care, or determine statutory compliance in any jurisdiction.

A deployment decision remains the responsibility of the organization and its designated accountable authorities.

# Foreword

A controlled deployment converts an approved AI system design into an operating service without losing traceability, safety constraints, security controls or accountability. This playbook provides a practical sequence from rollout planning through pilot, production release, stabilization, handover and post-deployment assurance.

# 1. Purpose and Scope

This playbook applies to new AI systems, material model upgrades, significant architecture changes, new agentic capabilities, external tool integrations, major data-source changes and physical-AI deployments.

It covers deployment preparation, release strategy, change approval, pilot execution, production transition, rollback, operational acceptance and continuing assurance. Minor routine changes may use a proportionate workflow where organizational change policy permits.

# 2. Deployment Principles

| Principle | Operational meaning |
| --- | --- |
| No production without scope | The deployed system, interfaces, data, users, suppliers and operating regions are explicitly defined. |
| No approval without evidence | Release decisions rely on current testing, risk and control evidence. |
| Progressive exposure | Increase users, traffic, autonomy and consequence only after stage-gate criteria are met. |
| Reversible change | Every material deployment has a tested rollback, disablement or safe-state path. |
| Separation of duties | Build, approval, deployment and independent assurance are appropriately separated. |
| Observe before expanding | Telemetry and human review are used to validate actual behavior before scale-up. |
| Known limitations remain visible | Residual risks, constraints and unsupported use cases are communicated to operators and users. |
| Failed evidence is retained | Negative, inconclusive and failed results remain part of the decision record. |

# 3. Rollout Model

| Stage | Deployment state | Primary objective | Exit gate |
| --- | --- | --- | --- |
| 0 | Plan | Define scope, strategy, ownership and deployment risk | Approved rollout plan |
| 1 | Prepare | Complete controls, evidence, runbooks and environments | Readiness review passed |
| 2 | Validate | Execute pre-production technical and operational testing | Validation evidence accepted |
| 3 | Pilot | Expose a limited population under heightened oversight | Pilot success criteria met |
| 4 | Limited production | Expand traffic with constraints and rapid rollback | Stability criteria met |
| 5 | General production | Operate at approved scope and service level | Operational acceptance |
| 6 | Stabilize | Monitor post-release behavior and close deployment findings | Stabilization review passed |
| 7 | Handover | Transfer ownership to business-as-usual operations | Signed operational acceptance |
| 8 | Sustain | Maintain continuing conformance and reassess material change | Recurring assurance |

# 4. Stage 0 — Plan the Deployment

## 4.1 Deployment plan minimum content

| Planning element | Required content |
| --- | --- |
| Release identifier | Unique release, build, model and configuration identifiers |
| Scope | Systems, environments, users, geographies, interfaces and suppliers |
| Change description | What is new, modified, removed or inherited |
| Risk classification | Security, safety, privacy, legal, operational and reputational impact |
| Rollout strategy | Pilot, canary, blue-green, phased region, feature flag or controlled cutover |
| Owners | Release owner, system owner, control owners and approvers |
| Success criteria | Functional, security, safety, quality and operational thresholds |
| Stop criteria | Conditions requiring pause, rollback, containment or escalation |
| Rollback | Technical and business rollback sequence |
| Monitoring | Telemetry, dashboards, alert thresholds and review cadence |
| Communications | Operator, user, customer, regulator and stakeholder notices |
| Evidence | Required deployment and decision artifacts |

## 4.2 Change impact assessment

Identify affected GAISSF controls and evidence packages.

Assess model, data, application, infrastructure, supplier and jurisdiction changes.

Determine whether prior testing remains valid.

Identify new or changed threat scenarios and failure modes.

Determine whether the Statement of Applicability, certification scope or public claims are affected.

Classify the change as routine, significant, major or emergency under organizational policy.

# 5. Stage 1 — Prepare the Release

| Workstream | Preparation activities | Required output |
| --- | --- | --- |
| Architecture | Confirm production topology, trust boundaries, access paths and dependencies | Approved architecture |
| Security | Harden environments, identities, secrets, network paths and logging | Security checklist |
| Data | Validate source, quality, lineage, privacy, retention and retrieval stores | Data readiness record |
| Model | Freeze model/version, provenance, configuration and evaluation baseline | Model release record |
| Application | Freeze prompt logic, orchestration, tools, policies and safeguards | Application release record |
| Operations | Prepare monitoring, support, incident, fallback and escalation runbooks | Operational runbooks |
| Evidence | Assemble release evidence and integrity records | Deployment evidence package |
| People | Train operators, support, approvers and affected users | Training record |

## 5.1 Environment controls

Separate development, test, staging and production environments.

Restrict production access using least privilege and privileged-access monitoring.

Use controlled configuration and secret-management processes.

Prevent unapproved model, prompt, data or tool changes after release freeze.

Synchronize release identifiers across code, model, configuration and evidence.

# 6. Stage 2 — Validate Before Production

| Validation area | Minimum validation objective | Evidence |
| --- | --- | --- |
| Functional | System performs approved use cases and rejects unsupported paths | Test results |
| Security | Threat scenarios and abuse cases are tested | Security evaluation |
| Robustness | Expected perturbations, malformed inputs and distribution changes are assessed | Robustness report |
| Privacy | Data flows, leakage, retention and user rights are verified | Privacy test record |
| Content safety | Harmful, prohibited and high-risk outputs are evaluated | Safety evaluation |
| Human oversight | Review, override and escalation mechanisms function | Oversight test |
| Resilience | Failover, recovery, degradation and rollback are tested | Resilience evidence |
| Observability | Required events, decisions and failures are logged | Telemetry verification |
| Physical safety | Safe state, override, actuation constraints and HIL/simulation are tested | Safety test package |

## 6.1 Pre-production gate

☐ All critical and high-risk test scenarios executed

☐ No unresolved release-blocking finding

☐ Residual risks documented and approved

☐ Evidence package complete and traceable

☐ Rollback tested

☐ Monitoring and alert thresholds verified

☐ Incident and communication runbooks exercised

☐ Release authority recorded

# 7. Stage 3 — Pilot Deployment

The pilot should limit exposure while producing representative evidence of actual operation. The pilot population, duration, transaction limits, autonomy, data and regions should be explicitly constrained.

| Pilot control | Recommended practice |
| --- | --- |
| Population | Select a controlled user group with informed support channels |
| Traffic | Limit requests, transactions or physical operating hours |
| Autonomy | Restrict tool calls, approvals and consequential actions |
| Data | Use approved data classes and enhanced leakage monitoring |
| Human review | Increase review frequency and require manual approval for high-impact outputs |
| Telemetry | Enable detailed logging and daily control-health review |
| Support | Provide rapid incident triage and direct operator escalation |
| Decision | Use pre-defined success, pause and failure criteria |

## 7.1 Pilot success criteria

| Criterion | Example decision measure |
| --- | --- |
| Control stability | No repeated control failure above approved tolerance |
| Security | No unresolved exploit path or material abuse pattern |
| Safety | No uncontained high-severity harmful outcome |
| Quality | Performance remains within approved operating range |
| Operations | Support and escalation operate within service targets |
| Observability | Required events are captured and attributable |
| User impact | Complaints, confusion and misuse remain within approved thresholds |
| Rollback | Rollback remains available and tested |

# 8. Stage 4 — Limited Production

Limited production expands real-world exposure while retaining enhanced controls. Expansion should be incremental and reversible.

| Expansion dimension | Control method |
| --- | --- |
| Users | Percentage-based or role-based enablement |
| Geography | Region-by-region activation |
| Features | Feature flags and capability allowlists |
| Traffic | Rate caps and transaction ceilings |
| Autonomy | Tiered approval and tool-permission limits |
| Data | Progressive enablement of data classes |
| Physical operation | Restricted locations, speeds, loads or operating windows |

## 8.1 Canary and blue-green patterns

| Pattern | Use | Control concern |
| --- | --- | --- |
| Canary | Expose a small percentage to the new release | Representative sampling and rapid rollback |
| Blue-green | Maintain old and new production stacks | Configuration parity and controlled cutover |
| Shadow | Run new system without affecting decisions | Data protection and non-action assurance |
| Feature flag | Enable selected capabilities independently | Flag governance and configuration evidence |
| Regional wave | Deploy by geography or business unit | Jurisdiction and dependency differences |

# 9. Stage 5 — General Production Release

## 9.1 Go-live decision package

| Decision input | Minimum content |
| --- | --- |
| Scope confirmation | Approved final production boundary |
| Control status | Applicable control implementation and open findings |
| Validation | Pre-production, pilot and limited-production results |
| Risk | Residual risks, exceptions and acceptance authority |
| Operations | Support, monitoring, incident, continuity and supplier readiness |
| Rollback | Current rollback point and safe-state confirmation |
| Communications | User disclosures and stakeholder notices |
| Approval | Named release authority, date and conditions |

## 9.2 Go-live checklist

☐ Release identifiers verified

☐ Production configuration matches approved baseline

☐ Monitoring dashboards active

☐ On-call and escalation contacts confirmed

☐ User and operator documentation published

☐ Supplier dependencies available

☐ Certificate and public claims reviewed where applicable

☐ Rollback point preserved

☐ Approval recorded before activation

# 10. Rollback, Containment and Safe-State Procedures

| Trigger | Immediate response | Decision owner |
| --- | --- | --- |
| Critical security exploit | Disable affected function, isolate systems and initiate incident response | Security incident authority |
| Material harmful output | Suspend feature, constrain model or require human approval | System owner / safety authority |
| Privacy breach | Contain data flow, revoke access and activate breach process | Privacy and incident authority |
| Loss of monitoring | Pause expansion or revert to last observable release | Operations owner |
| Model degradation | Revert model/configuration or restrict use cases | Model owner |
| Supplier outage/change | Fail over, degrade safely or suspend dependent capability | Service owner |
| Physical safety threshold breach | Enter safe state and stop actuation | Safety authority |

## 10.1 Rollback record

Trigger and detection time

Affected release and scope

Decision authority

Actions taken

Data and transaction handling

Customer or regulator notification

Evidence preserved

Recovery validation

Root-cause and corrective-action reference

# 11. Stage 6 — Stabilization

| Time window | Primary activities |
| --- | --- |
| First 24 hours | Continuous telemetry review, incident watch, rollback readiness and release verification |
| Days 2-7 | Daily control-health review, user feedback, supplier and performance monitoring |
| Weeks 2-4 | Trend analysis, finding closure, evidence consolidation and operational tuning |
| End of stabilization | Formal review of success criteria, residual risk and handover readiness |

## 11.1 Stabilization review questions

Did actual use remain within approved scope?

Did any control fail, degrade or require manual compensation?

Were alerts actionable and reviewed?

Did user behavior reveal new misuse or confusion?

Did suppliers or data sources change?

Did the release affect certification scope or public claims?

Are operational teams ready to accept ownership?

# 12. Stage 7 — Operational Handover

| Handover item | Acceptance evidence |
| --- | --- |
| Ownership | Named system, service, model, data and control owners |
| Runbooks | Approved operating, incident, fallback and recovery procedures |
| Monitoring | Dashboards, alerts, thresholds and review responsibilities |
| Access | Production roles and privileged-access review |
| Evidence | Repository, index, retention and refresh ownership |
| Suppliers | Escalation, support, notification and continuity contacts |
| Training | Operator and support competence records |
| Backlog | Known defects, improvements and corrective actions |
| Risk | Residual-risk and exception register |
| Acceptance | Signed operational acceptance record |

# 13. Stage 8 — Sustain and Improve

| Trigger | Required reassessment |
| --- | --- |
| Model version change | Provenance, regression, security, safety and performance |
| Prompt/orchestration change | Abuse, authorization, output and workflow testing |
| New tool or agent | Permissions, transactions, delegation and containment |
| New data source | Lineage, privacy, quality, poisoning and licence |
| Infrastructure change | Hardening, identity, segmentation, resilience and logging |
| New jurisdiction | Legal, regulatory, data-transfer and disclosure analysis |
| Incident or near miss | Control effectiveness, root cause and corrective action |
| GAISSF release | Version impact and migration assessment |

# 14. Deployment Roles and Decision Rights

| Role | Deployment responsibility |
| --- | --- |
| Executive sponsor | Resolve material scope, funding and risk issues |
| Release authority | Approve or reject production activation |
| System owner | Own business use, scope and residual risk |
| Security lead | Approve security readiness and containment |
| Safety lead | Approve safety case and physical-AI constraints where applicable |
| Model owner | Own model provenance, evaluation and version |
| Data owner | Approve data use, quality, privacy and retention |
| Operations lead | Accept monitoring, support and continuity |
| Independent assurance | Challenge evidence and gate decisions |
| Change manager | Maintain release and rollback records |

# 15. Deployment Evidence Package

| Evidence group | Artifacts |
| --- | --- |
| Planning | Deployment plan, scope, strategy, impact assessment |
| Build | Release manifests, model/data/configuration identifiers |
| Validation | Functional, security, safety, privacy and resilience tests |
| Approval | Gate decisions, exceptions and residual-risk acceptance |
| Execution | Deployment logs, feature-flag records and environment evidence |
| Pilot | Pilot metrics, issues, reviews and decision record |
| Production | Go-live checklist, activation record and monitoring evidence |
| Stabilization | Control-health reviews, incidents and corrective actions |
| Handover | Operational acceptance and owner acknowledgements |
| Integrity | Hashes, signatures, timestamps and repository audit records |

# 16. Deployment Metrics

| Metric | Use | Caution |
| --- | --- | --- |
| Deployment success rate | Track release reliability | Do not hide severity of failed releases |
| Rollback frequency | Detect instability or weak validation | Some rollback use demonstrates control effectiveness |
| Time to detect | Evaluate observability | Depends on event visibility |
| Time to contain | Evaluate incident readiness | Measure by severity class |
| Control-health failures | Identify operational degradation | Normalize by volume and scope |
| Pilot-to-production defects | Evaluate pilot representativeness | Classify materiality |
| Unapproved configuration drift | Detect release-control weakness | Requires authoritative baseline |
| Evidence completeness | Assess deployment traceability | Count does not equal quality |

# 17. Emergency Deployment Procedure

Emergency deployment may shorten normal sequencing but shall not eliminate accountability, logging, rollback, risk acceptance or retrospective review.

1.    Document the emergency condition and affected scope.

2.    Identify minimum mandatory validation and containment.

3.    Obtain authorized emergency approval.

4.    Preserve the pre-change state and rollback option.

5.    Enable enhanced monitoring.

6.    Complete omitted documentation and testing after stabilization.

7.    Conduct retrospective review and corrective action.

# 18. Common Deployment Failure Modes

| Failure mode | Consequence | Prevention |
| --- | --- | --- |
| Uncontrolled model update | Evidence and behavior no longer match approval | Pin versions and enforce release manifests |
| Pilot not representative | Production failures appear after scale-up | Select realistic users, data and workloads |
| Rollback untested | Containment fails during incident | Test rollback before release |
| Telemetry activated late | Early failures are invisible | Verify observability before pilot |
| Feature flags unmanaged | Unauthorized capabilities become active | Control flag ownership and logging |
| Supplier change unnoticed | Inherited controls silently change | Contractual notification and dependency monitoring |
| Handover assumed | No team owns post-release risks | Require signed operational acceptance |
| Success-only reporting | Negative evidence is lost | Retain failed and inconclusive results |

# 19. Limitations

This playbook does not prescribe a universal rollout duration.

It does not replace sector-specific safety, quality or regulatory release processes.

A successful pilot does not prove absence of low-frequency or emerging failures.

Rollback may be constrained where irreversible transactions or physical actions occur.

Deployment evidence remains subject to sampling, completeness and integrity limitations.

# 20. Notably Absent

No authorization to deploy merely because a checklist is complete.

No assumption that canary deployment is safe for every high-consequence system.

No waiver of human oversight, risk acceptance or incident obligations.

No promise that progressive rollout prevents all harmful outcomes.

No substitution for independent physical-safety validation.

No permission to erase failed deployment evidence.

# Annex A — Deployment Plan Template

| Field | Entry |
| --- | --- |
| Release identifier |  |
| Scope |  |
| Change description |  |
| Risk classification |  |
| Rollout strategy |  |
| Owners |  |
| Success criteria |  |
| Stop criteria |  |
| Rollback |  |
| Monitoring |  |
| Communications |  |
| Evidence |  |
| Approval |  |

# Annex B — Stage-Gate Record

| Gate | Criteria met | Open issues | Decision | Approver | Date |
| --- | --- | --- | --- | --- | --- |
| Plan |  |  |  |  |  |
| Prepare |  |  |  |  |  |
| Validate |  |  |  |  |  |
| Pilot |  |  |  |  |  |
| Limited production |  |  |  |  |  |
| General production |  |  |  |  |  |
| Stabilization |  |  |  |  |  |
| Handover |  |  |  |  |  |

# Annex C — Rollback Checklist

☐ Rollback authority confirmed

☐ Last known good release available

☐ Data and transaction consequences assessed

☐ Supplier dependencies addressed

☐ Monitoring active during rollback

☐ Users and stakeholders notified

☐ Evidence preserved

☐ Recovery validation completed

☐ Root-cause review initiated

# Annex D — Operational Acceptance Template

| Acceptance area | Status | Evidence | Owner sign-off |
| --- | --- | --- | --- |
| Monitoring |  |  |  |
| Incident response |  |  |  |
| Support |  |  |  |
| Access and privileges |  |  |  |
| Evidence maintenance |  |  |  |
| Supplier management |  |  |  |
| Known risks and exceptions |  |  |  |
| Training |  |  |  |

# Annex E — Source Traceability

| Playbook subject | Controlled source |
| --- | --- |
| Normative requirements | GAISSF-NOR-001 |
| Control records | GAISSF-NOR-004 |
| Terminology | GAISSF-NOR-005 |
| Release status | GAISSF-NOR-007 |
| Historical decisions | GAISSF-NOR-008 |
| Adoption program | GAISSF-IMP-009 |
| Implementation architecture and workflows | GAISSF-IMP-010 |

# Annex F — Publication Record

| Version | Date | Change | Status |
| --- | --- | --- | --- |
| 1.0 | 29 June 2026 | Initial deployment playbook for GAISSF v1.0 | Final Publication Edition |

# Controlled Profile Reconciliation Notice

The Foundational profile comprises 52 controls across all nine domains, as enumerated in the controlled conformance profile. Seven controls are excluded from that profile; the exclusions are not equivalent to excluding the D9 domain.

Any earlier wording that described the Foundational profile as D1-D8 only or treated the entire D9 domain as excluded is superseded by this statement and the controlled conformance profile.

# Detailed Rollout Work Breakdown

| Work package | Tasks | Owner | Exit evidence |
| --- | --- | --- | --- |
| Release planning | Scope, risk, strategy, schedule, dependencies | Release manager | Approved plan |
| Environment preparation | Access, secrets, network, logging, baseline | Platform owner | Environment checklist |
| Validation | Functional, security, safety, privacy, resilience | Test lead | Signed validation report |
| Pilot | Users, limits, oversight, support, telemetry | System owner | Pilot decision record |
| Scale-up | Traffic, feature, region and autonomy waves | Operations lead | Wave gate approvals |
| Handover | Runbooks, ownership, training and backlog | Service owner | Operational acceptance |

# Decision Trees for Pause and Rollback

A pause is appropriate when evidence is incomplete, monitoring is impaired or a threshold breach has not created immediate material exposure. Rollback or safe-state activation is appropriate when a material security, safety, privacy or integrity condition exists and continued operation increases harm.

| Condition | Default decision |
| --- | --- |
| Critical exploit or unsafe actuation | Contain and roll back or enter safe state |
| Material harmful output with uncertain scope | Pause affected capability and investigate |
| Monitoring unavailable for high-risk action | Restrict or suspend until observability returns |
| Minor performance degradation within risk tolerance | Continue under enhanced monitoring |
| Supplier model change without evaluation | Hold expansion and revalidate |

# Communications Plan

| Audience | Message content | Trigger |
| --- | --- | --- |
| Operators | Release, known limitations, monitoring and escalation | Before activation |
| Users | Capability, restrictions, disclosures and recourse | Before access |
| Executives | Risk, residual issues and go/no-go decision | Each material gate |
| Customers | Service impact and material change | Contractual trigger |
| Regulators | Required incident or change information | Legal trigger |

# Post-Deployment Validation

Compare actual traffic and users with approved scope.

Re-run critical tests against production configuration.

Validate alert completeness and operator response.

Review user feedback and unexpected use.

Confirm evidence package matches the deployed release.

Close or reclassify pilot and stabilization findings.

# Publication Completeness and Intended Use

This full publication edition of GAISSF-IMP-011 is designed to stand on its own for its stated role: complete execution playbook from planning through production handover. It includes purpose, scope, governance, operating guidance, evidence expectations, limitations, decision criteria and reusable records appropriate to that role.

Completeness does not mean that the document replaces the normative control statements, applicable law, sector-specific engineering, organizational procedures or professional judgement. Cross-referenced GAISSF documents remain part of the controlled document system.

| Completeness dimension | Treatment in this edition |
| --- | --- |
| Normative alignment | Reconciled to the authoritative 59-control baseline and controlled profile structure. |
| Operational usability | Includes roles, workflows, gates, evidence, metrics, escalation and examples where relevant. |
| Traceability | Identifies dependencies and preserves the distinction between requirements, guidance and examples. |
| Limitations | States what the document does not establish or guarantee. |
| Maintenance | Includes review triggers, change control and publication status. |

# Legal and Regulatory Integration

GAISSF provides an operational security, safety, governance and evidence framework. It does not determine which laws apply, establish statutory compliance, create a legal safe harbour, define a legal standard of care, replace competent legal advice, or guarantee that evidence collected for GAISSF purposes will satisfy a regulator, court or other authority. Organizations should maintain a jurisdiction-specific legal and regulatory obligations register and map applicable obligations to their GAISSF scope, controls, evidence, reporting processes and decision authorities.

## Legal and regulatory interface requirements

Identify applicable jurisdictions, regulators, sector rules, contractual duties and internal legal authorities before relying on this guide.

Maintain a controlled obligations register, reporting-clock register, retention schedule, legal-hold process and conflicts-of-obligation procedure.

Treat statutory, regulatory and contractual analysis as a parallel workstream to GAISSF implementation and assurance.

Record the legal basis, responsible owner, scope, decision, evidence, deadline and review date for each material obligation.

Do not represent GAISSF conformance, maturity or certification as legal approval, permission to operate, immunity from enforcement or proof that harm cannot occur.

# How to use this document

| Reader | Recommended use |
| --- | --- |
| Executive or board reader | Review purpose, decision rights, legal and regulatory integration, limitations and Notably Absent sections. |
| Program or control owner | Use workflows, templates, gates, evidence fields and escalation criteria as implementation aids. |
| Engineering or operations team | Translate guidance into system-specific procedures, configurations, runbooks and testable acceptance criteria. |
| Legal, privacy or compliance team | Validate jurisdiction-specific obligations, deadlines, retention, disclosure, privilege and regulator-facing requirements. |
| Assessor or auditor | Use the document as informative context only; test claims against the authoritative normative sources and applicable assessment criteria. |

# See Also

GAISSF-IMP-010 for engineering controls.

GAISSF-IMP-014 for run-state operations.

GAISSF-IMP-016 for troubleshooting and containment.

# Deployment-specific regulatory enhancements

## Parallel regulatory notification decision path

Contain immediate harm and preserve relevant evidence.

Notify legal, privacy, compliance and regulatory-response owners.

Determine applicable incident, breach, safety, securities, sector and contractual regimes.

Start and record each potentially applicable reporting clock.

Identify authorities, customers, data subjects and counterparties.

Approve initial, supplemental and final communications.

Document the decision to notify or not notify, supporting facts, uncertainty and approver.

Illustrative deadlines are jurisdiction- and event-specific. For example, GDPR supervisory-authority notification may require action within 72 hours after awareness where Article 33 applies; NIS2 uses staged notifications for covered significant incidents; SEC Form 8-K timing generally runs from a registrant’s materiality determination, not automatically from incident occurrence; EU AI Act serious-incident timing varies by incident category and system context. Legal owners shall validate the applicable rule.

## Consumer-protection and public-claim release gate

Substantiate capability, performance, safety and autonomy claims.

Confirm that terms, privacy notices, automated-decision disclosures and limitations match actual operation.

Assess unfair, deceptive, dark-pattern, accessibility and vulnerable-user risks.

Verify required consent, authorization and customer communication.

## Material-change external impact assessment

| External artifact or obligation | Assessment question |
| --- | --- |
| Conformity assessment or registration | Does the change alter the approved system, intended purpose or risk classification? |
| Regulatory filing or notification | Must an existing filing be amended or a new notice made? |
| Customer commitment | Does the change invalidate a representation, SLA, warranty or approved use? |
| Certification scope | Does the change exceed the assessed configuration or evidence period? |
| Insurance or safety case | Does the change affect coverage conditions, hazard analysis or approved controls? |

## Pilot, canary, supplier cutover and handover

Use representative, minimized and authorized pilot data; preserve comparison with the validated baseline.

Define canary stages and tolerances by risk; fixed percentages and dwell times are illustrative only.

Maintain supplier fallback while validating a new endpoint, dependency or service.

Require operational teams to demonstrate log retrieval, alert testing, rollback execution and escalation before acceptance.

## Notably Absent — legal and regulatory boundary

No automatic stop rule where continued operation is necessary for safety, critical service or evidence preservation.

No universal incident-reporting deadline.

No assumption that internal reassessment alone preserves external filings or approvals.

# Publication revision record

| Revision | Disposition |
| --- | --- |
| R2 — Regulatory and practitioner refinement | Added legal and regulatory integration, preservation, reporting, decision-record, public-claim and usability guidance. No normative GAISSF control was added, removed, renamed or amended. |
| Authority boundary | GAISSF-NOR-001, GAISSF-NOR-004 and controlled profile records remain authoritative. |