## Document Control
Field | Value
Document | Implementation Workbook
ID / Version | SEC-042 / 1.1
Status | Refined Controlled Pre-Release
Baseline | 59 controls, including 7 D9 controls
Testing boundary | No uncontrolled adversarial testing on live production actuation paths.
Open review gates | OT/ICS, functional safety, subsector, legal/regulatory, accessibility and publication QA.
Notably Absent | No automatic compliance, SIL, deterministic-timing or universal-likelihood claim.

## Day 1 Triage
Priority | Action | Control Focus | Owner | Due | Status | Evidence
1 | Inventory AI-enabled assets, embedded vendor AI and actuation interfaces. | D4-CTL-01; D4-CTL-06 |  |  | Not Started
2 | Identify CI-3/4/5 systems and prohibit unapproved write/autonomous authority. | D6-CTL-01; D9-CTL-01 |  |  | Not Started
3 | Verify override, emergency stop and safe-state behaviour. | D9-CTL-02; D9-CTL-03 |  |  | Not Started
4 | Establish digital twin/HIL/isolated testing boundary. | D1; D2; D9 |  |  | Not Started
5 | Establish air-gap transfer manifest and cryptographic verification. | CI-EV-024 |  |  | Not Started
6 | Record black-box supplier assertions and independent boundary-test plan. | D1-CTL-01; D4-CTL-01 |  |  | Not Started
7 | Measure latency impact of AI controls and monitors. | CI-EV-026 |  |  | Not Started
8 | Confirm local fallback and cloud/API dependencies. | D9-CTL-02 |  |  | Not Started

## AI System Register
System ID | Name | Subsector | Purpose | IT/OT/ICS Zone | Authority Pattern | CI Class | Existing SIL/LOPA Rating | Safety Layer Role | Vendor Opacity | Fallback | Owner | Status | Evidence
[ID] | [Name] | Energy/Water/Healthcare/Other |  |  | Advisory | CI-1 |  | Advisory / Prevention / Mitigation / None | Unknown |  |  | Proposed

## Criticality Classification
System ID | Consequence | Autonomy | Speed | Reversibility | Detectability | Concentration | Fallback Weakness | Uncertainty | Total | Indicative Class | Approved Class | Rationale | Threshold | Max Score
[ID] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | CI-1 | CI-1 |  | CI-1 | 12
[9 empty] | 0 | CI-1 |  |  | CI-2 | 19
[9 empty] | 0 | CI-1 |  |  | CI-3 | 26
[9 empty] | 0 | CI-1 |  |  | CI-4 | 33
[9 empty] | 0 | CI-1 |  |  | CI-5 | 40
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1
[9 empty] | 0 | CI-1

## Control Implementation
Control ID | Control Title | Recommended Priority | Status | Owner | Evidence IDs | Evidence Tier | Design Effective | Operating Effective | Finding | Corrective Action | Completion % | RAG | Notably Absent
D1-CTL-01 | DATASET PROVENANCE & POISONING PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Detection of novel poisoning methods not represented in the approved test corpus; assurance against an authorized insider able to alter both data and trusted provenance records; proof that source allowlisting establishes semantic correctness.
D1-CTL-02 | MODEL EXTRACTION RESISTANCE | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee that rate limits or output controls prevent all model inference; proof that protected model logic cannot be approximated through physical-process observation or compromised vendor tooling.
D1-CTL-03 | BEHAVIORAL DRIFT DETECTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal drift threshold; assurance that statistically stable behaviour remains operationally safe; detection of changes hidden by sensor faults, seasonal shifts or coordinated manipulation.
D1-CTL-04 | FEDERATED LEARNING POISONING PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D1-CTL-05 | EMBEDDING SPACE ROBUSTNESS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D1-CTL-06 | POST-QUANTUM MODEL SIGNING & CRYPTO HARDENING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D1-CTL-07 | LORA/ADAPTER INTEGRITY VERIFICATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D1-CTL-08 | MODEL MERGE ATTACK DETECTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D1-CTL-09 | QUANTIZATION BACKDOOR SCREENING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D2-CTL-01 | DIRECT PROMPT INJECTION PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Protection against every semantic or multimodal jailbreak; permission to test adversarial payloads against live production control paths; assurance that pattern matching alone blocks novel attacks.
D2-CTL-02 | INDIRECT PROMPT INJECTION PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Protection against every semantic or multimodal jailbreak; permission to test adversarial payloads against live production control paths; assurance that pattern matching alone blocks novel attacks.
D2-CTL-03 | JAILBREAK RESISTANCE TESTING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D2-CTL-04 | MULTI-MODAL INJECTION DEFENSE | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D2-CTL-05 | FUNCTION CALL/TOOL CALL INJECTION PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D2-CTL-06 | CROSS-CONTEXT HIJACKING MITIGATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-01 | LEAST AGENCY ENFORCEMENT | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-02 | INTER-AGENT COMMUNICATION SECURITY | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-03 | AGENTIC PROMPT CHAINING DETECTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-04 | EMBODIED AI SAFETY CONTROLS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-05 | MULTI-AGENT TRUST CHAIN ATTESTATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | An assumption of continuous external connectivity or cloud control-plane access; a requirement to deploy SPIFFE/SPIRE where offline hardware identity, signed manifests or physical controls provide a justified equivalent.
D3-CTL-06 | PERSISTENT MEMORY EXFILTRATION PREVENTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D3-CTL-07 | SECURE MEMORY LIFECYCLE MANAGEMENT | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D4-CTL-01 | AI BILL OF MATERIALS (AI BOM) MAINTENANCE | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | An assumption that suppliers disclose model weights or training data; acceptance of vendor assertions as conclusive evidence where independent boundary testing is feasible.
D4-CTL-02 | MODEL FILE & ARTIFACT SCANNING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D4-CTL-03 | MODEL HUB & REGISTRY VETTING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D4-CTL-04 | MCP SERVER BEHAVIORAL MONITORING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D4-CTL-05 | THIRD-PARTY AI API SECURITY ASSESSMENT | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D4-CTL-06 | SHADOW AI DISCOVERY & GOVERNANCE | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Visibility into every offline engineering workstation, removable-media workflow or embedded vendor feature; authorization to deploy discovery agents where they could affect validated OT configurations.
D4-CTL-07 | AI SOFTWARE COMPOSITION ANALYSIS (SCA) | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A guarantee against zero-day attack paths, authorized-insider misuse or failures outside the tested system boundary; proof of safety, legal compliance or operating effectiveness from design evidence alone.
D5-CTL-01 | HARMFUL CONTENT BLOCKING | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D5-CTL-02 | PII LEAKAGE PREVENTION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D5-CTL-03 | COPYRIGHT DETECTION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D5-CTL-04 | AI WATERMARKING ROBUSTNESS | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D5-CTL-05 | PRIVACY-BY-DESIGN VERIFICATION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D5-CTL-06 | PRIVACY-PRESERVING ML VALIDATION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A universal definition of harmful content; assurance that filtering prevents misleading but superficially benign operational instructions; permission for generated content to replace approved operating procedures.
D6-CTL-01 | HUMAN-IN-THE-LOOP FOR HIGH-RISK ACTIONS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-02 | AUDIT TRAIL COMPLETENESS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-03 | AI MODEL CARD COMPLETENESS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-04 | AI INCIDENT RESPONSE READINESS | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-05 | MODEL DEPRECATION & DECOMMISSIONING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-06 | THIRD-PARTY AI VENDOR GOVERNANCE | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D6-CTL-07 | AI RESILIENCE & BUSINESS CONTINUITY | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Proof that a nominal human-in-the-loop has time, competence, information and authority to intervene; assurance that an override remains usable during alarm floods or degraded communications.
D7-CTL-H01 | AI-GENERATED PHISHING SIMULATION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A substitute for human-factors engineering, staffing analysis, accessibility assessment or process-safety review; evidence that absence of complaints means absence of harm.
D7-CTL-H02 | DEEPFAKE DETECTION TRAINING | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A substitute for human-factors engineering, staffing analysis, accessibility assessment or process-safety review; evidence that absence of complaints means absence of harm.
D7-CTL-H03 | OUT-OF-BAND AUTHENTICATION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A substitute for human-factors engineering, staffing analysis, accessibility assessment or process-safety review; evidence that absence of complaints means absence of harm.
D7-CTL-H04 | AI SOCIAL ENGINEERING IR | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A substitute for human-factors engineering, staffing analysis, accessibility assessment or process-safety review; evidence that absence of complaints means absence of harm.
D7-CTL-H05 | AI-ENHANCED EXTERNAL ATTACK DEFENSE | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A substitute for human-factors engineering, staffing analysis, accessibility assessment or process-safety review; evidence that absence of complaints means absence of harm.
D8-CTL-01 | EU AI ACT RISK TIER MAPPING | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A claim of legal equivalence, certification reciprocity or automatic compliance with any cited framework; jurisdiction-specific legal advice.
D8-CTL-02 | ISO 42001 GAP ANALYSIS | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A claim of legal equivalence, certification reciprocity or automatic compliance with any cited framework; jurisdiction-specific legal advice.
D8-CTL-03 | GPAI TECHNICAL DOCUMENTATION VERIFICATION | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A claim of legal equivalence, certification reciprocity or automatic compliance with any cited framework; jurisdiction-specific legal advice.
D8-CTL-04 | DORA ICT INCIDENT REPORTING (FINANCIAL SECTOR) | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A claim of legal equivalence, certification reciprocity or automatic compliance with any cited framework; jurisdiction-specific legal advice.
D8-CTL-05 | NIST SP 800-218A COMPLIANCE CHECK | High | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | A claim of legal equivalence, certification reciprocity or automatic compliance with any cited framework; jurisdiction-specific legal advice.
D9-CTL-01 | PHYSICAL HARM BOUNDARY ENFORCEMENT | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-02 | SAFE STATE AND GRACEFUL DEGRADATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-03 | HUMAN OVERRIDE AND EMERGENCY STOP | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-04 | CYBER-PHYSICAL ATTACK DETECTION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-05 | PHYSICAL ENVIRONMENT INTEGRITY MONITORING | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-06 | ACTUATOR COMMAND VERIFICATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.
D9-CTL-07 | PHYSICAL INCIDENT EVIDENCE PRESERVATION | Critical | Requires Assessment |  |  | {"CI-1": "T1 design evidence or T2 implemented configuration", "CI-2": "T2 implementation evidence plus representative test", "CI-3": "T3 controlled simulation or independently witnessed test", "CI-4": "T3 high-fidelity simulation/HIL plus operating evidence", "CI-5": "T3/T4 independent safety/security assurance; live destructive testing is not presumed"} | Not Assessed | Not Assessed |  |  | 0 | Amber | Replacement of HAZOP, FMEA, LOPA, SIF/SIL engineering, hardware interlocks or statutory process-safety duties; a guarantee that AI security monitors preserve deterministic timing without measured latency evidence.

## Evidence Register
Evidence ID | Evidence Item | System ID | Control IDs | Grade | Tier | Owner | Location | Version/Period | Status | Limitations | Next Review
CI-EV-001 | AI system and dependency register |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-002 | Approved system boundary and architecture |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-003 | CI criticality assessment |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-004 | Authority and action matrix |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-005 | Model/data provenance record |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-006 | AI/asset BOM and supplier dependency record |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-007 | Threat model |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-008 | Safety and operational impact assessment |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-009 | Validation plan |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-010 | Validation results |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-011 | Adversarial test report |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-012 | Access and privilege review |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-013 | Configuration baseline |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-014 | Monitoring and alert evidence |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-015 | Drift report |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-016 | Incident record |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-017 | Fallback and rollback exercise |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-018 | Change approval and revalidation |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-019 | Supplier assurance pack |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-020 | Training and competence records |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-021 | Exception and residual-risk acceptance |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-022 | Independent assessment report |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-023 | Digital Twin / HIL Shadow Environment Certification |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-024 | Air-Gap Transfer Manifest and Cryptographic Verification Log |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-025 | Safety-Instrumented Function Override Audit Log |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.
CI-EV-026 | Latency Impact Assessment |  |  | G1 Design; G2 Implemented; G3 Operating effectiveness; G4 Independent assurance. | T1 primary record; T2 verified secondary/vendor evidence; T3 controlled simulation/HIL; T4 independent assurance. |  |  |  | Not Reviewed | Verify provenance, scope, integrity, reproducibility, limitations and relation to the tested control.

## Threat Register
Threat ID | Threat | System ID | Controls | Likelihood | Impact | Risk Score | Priority | Owner | Coverage | Status | Mitigation | Evidence Boundary
CI-THR-001 | Manipulated sensor data |  | D1-CTL-01; D1-CTL-03; D9-CTL-05 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | OT engineering / CISO | Partial until system-level assessment | Open | Redundant sensing, hardware plausibility checks, signed telemetry and source validation. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-002 | Training-data poisoning |  | D1-CTL-01; D1-CTL-04 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Data owner / CISO | Partial until system-level assessment | Open | Approved sources, cryptographic manifests, isolated scanning and dual authorization. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-003 | Compromised model update |  | D1-CTL-04; D3-CTL-05; D4-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Model owner / OT engineering | Partial until system-level assessment | Open | Signed updates, offline verification, staged deployment and rollback. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-004 | Prompt injection affecting operator assistant |  | D2-CTL-01; D2-CTL-02; D6-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / operations | Partial until system-level assessment | Open | Isolated testing, grounded sources, read-only tools and approval before operational action. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-005 | Indirect prompt injection |  | D2-CTL-01; D2-CTL-02; D5-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / application owner | Partial until system-level assessment | Open | Content provenance, retrieval isolation, tool allowlists and source labeling. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-006 | Unauthorized tool execution |  | D2-CTL-03; D3-CTL-01; D6-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / system owner | Partial until system-level assessment | Open | Least privilege, pre-execution authorization, command allowlists and immutable logs. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-007 | Excessive agent permissions |  | D2-CTL-03; D3-CTL-01; D4-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / system owner | Partial until system-level assessment | Open | Time-bounded credentials, segregation of duties and authority matrix. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-008 | Cloud/API outage |  | D4-CTL-01; D4-CTL-04; D9-CTL-02 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Resilience lead / operations | Partial until system-level assessment | Open | Local fallback, cached approved models, dependency monitoring and manual operation. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-009 | Model drift or concept drift |  | D1-CTL-03; D6-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Model owner / operations | Partial until system-level assessment | Open | Operational thresholds, redundant indicators, review and safe suspension. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-010 | Automation bias and alarm suppression |  | D6-CTL-01; D7-CTL-01; D7-CTL-02 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Operations / human factors | Partial until system-level assessment | Open | Alarm-management testing, shift training, sampled unfiltered views and override drills. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-011 | Common-mode model failure across sites |  | D1-CTL-03; D4-CTL-01; D9-CTL-02 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Enterprise architecture / resilience | Partial until system-level assessment | Open | Diversity, phased rollout, site isolation and cross-site stop criteria. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-012 | Unsafe AI-generated code/configuration |  | D2-CTL-03; D4-CTL-03; D9-CTL-06 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Engineering authority / CISO | Partial until system-level assessment | Open | Offline review, simulation, signed change control and command verification. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-013 | Loss of audit logging |  | D4-CTL-05; D9-CTL-07 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / evidence custodian | Partial until system-level assessment | Open | Local tamper-evident logging, time synchronization and offline export. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-014 | Opaque supplier AI component |  | D1-CTL-01; D4-CTL-01; D8-CTL-03 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Procurement / system owner | Partial until system-level assessment | Open | Vendor assertion register, independent boundary tests, contract controls and residual-risk acceptance. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-015 | Unauthorized shadow AI |  | D4-CTL-06; D3-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | CISO / site manager | Partial until system-level assessment | Open | Asset discovery adapted to validated OT, removable-media controls and approved alternatives. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-016 | Emergency-mode failure |  | D6-CTL-01; D9-CTL-02; D9-CTL-03 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Operations / safety lead | Partial until system-level assessment | Open | Simulator exercises, independent override, staffing and emergency procedures. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-017 | Sensor spoofing |  | D9-CTL-04; D9-CTL-05; D1-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | OT engineering / safety lead | Partial until system-level assessment | Open | Redundant diverse sensors, plausibility checks, authenticated telemetry and physical inspection. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-018 | Actuator command injection |  | D9-CTL-01; D9-CTL-06; D3-CTL-01 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | OT engineering / CISO | Partial until system-level assessment | Open | Independent command validation, hard authority limits, signed commands and interlocks. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-019 | Safety monitor bypass |  | D9-CTL-01; D9-CTL-03; D9-CTL-07 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Functional safety lead | Partial until system-level assessment | Open | Separation, tamper detection, protected maintenance mode and override evidence. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-020 | Adversarial physical input |  | D2-CTL-04; D9-CTL-04; D9-CTL-05 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Engineering / security testing | Partial until system-level assessment | Open | Environmental robustness tests, sensor diversity and safe rejection behavior. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-021 | Sensor calibration drift |  | D1-CTL-03; D9-CTL-05 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Maintenance / engineering | Partial until system-level assessment | Open | Calibration governance, cross-sensor comparison and maintenance escalation. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.
CI-THR-022 | Compromised OT hardware or firmware |  | D4-CTL-01; D3-CTL-05; D9-CTL-06 | Not Assessed | System-specific 1-5 assessment required | Not calculated until organization assigns likelihood and impact | Determine from local consequence and exposure | Supply chain / CISO | Partial until system-level assessment | Open | Supplier assurance, signed firmware, secure custody, boundary monitoring and replacement plan. | Public, verified telemetry on AI-specific OT incidents remains incomplete; no quantitative likelihood is assigned.

## Supplier Register
Supplier ID | Supplier | Component | Systems | Risk Rating | Vendor Assertion | Independent Boundary Test | Evidence Gaps | Continuity/Exit | Owner | Status | Next Review

## Exceptions
Exception ID | System ID | Control ID | Gap | Compensating Control | Residual Risk | Owner | Approver | Raised | Review Due | Escalation Date | Status | Evidence

## Incident Register
Incident ID | System ID | Detected | Severity | Description | Physical/Safety Impact | Containment | Fallback | Evidence Preserved | Notification Decision | Recovery | Root Cause | Actions | Status

## Model Change Register
Change ID | System ID | Change Type | Description | Risk Impact | Test Boundary | Latency Test | Rollback | Approvals | Deployment | Revalidation | Status | Evidence

## Training Matrix
Role | Module | System/Subsector | Required | Completed | Assessment | Expiry | Evidence

## Audit Trail
Entry ID | Timestamp | User/Role | Sheet/Record | Change | Reason | Approval/Evidence

## Control Dependency Map
Control ID | Depends On | Dependency Type | Rationale | Sequence

## 90-Day Roadmap
Phase | Action | Control Scope | Owner | Output | Completion Criterion | Priority | Status | Due | Evidence